## Spring
Group 45 Timeline | [10 empty] | https://goo.gl/PXLbMe
Minjae Lee, Youngho Lim, Karishma Rana, Joshua Ng, Kayla Hunt
PROJECT TITLE | Predicting Success of Crowdfunding Projects on Kickstarter
[33 empty] | MIDTERM REPORT | [34 empty] | FINAL REPORT
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Team Composition | All | 2022-01-31 | 2022-02-01 | 1 | 2022-03-21 M: Spring Break
Project Proposal
Introduction & Background | Kayla Hunt | 2022-02-02 | 2022-02-18 | 16 | bar: 2022-01-31 W to 2022-02-14 F
Problem Definition | Kayla Hunt | 2022-02-02 | 2022-02-18 | 16 | bar: 2022-01-31 W to 2022-02-14 F
Methods | Youngho Lim, Minjae Lee | 2022-02-02 | 2022-02-18 | 16 | bar: 2022-01-31 W to 2022-02-14 F
Potential Dataset | Youngho Lim | 2022-02-02 | 2022-02-18 | 16 | bar: 2022-01-31 W to 2022-02-14 F
Potential Results & Discussion | Joshua Ng | 2022-02-02 | 2022-02-18 | 16 | bar: 2022-01-31 W to 2022-02-14 F
Video Creation & Recording | Karishma Rana | 2022-02-18 | 2022-02-24 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 R
GitHub Page | Joshua Ng | 2022-02-10 | 2022-02-15 | 5 | bar: 2022-02-07 R to 2022-02-14 T
Midterm Report
Model 1 (M1) Design & Selection | All | 2022-02-25 | 2022-02-28 | 3 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-21 F to 2022-02-28 M
M1 Data Cleaning | Karishma Rana | 2022-02-25 | 2022-03-05 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-21 F to 2022-02-28 S
M1 Data Visualization | Youngho Lim | 2022-02-25 | 2022-03-05 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-21 F to 2022-02-28 S
M1 Feature Reduction | Kayla Hunt | 2022-02-25 | 2022-03-05 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-21 F to 2022-02-28 S
M1 Implementation & Coding | Youngho Lim | 2022-03-05 | 2022-03-19 | 14 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-28 S to 2022-03-14 S
M1 Results Evaluation | Joshua Ng | 2022-03-18 | 2022-03-20 | 2 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 F to 2022-03-14 U
Model 2 (M2) Design & Selection | All | 2022-03-07 | 2022-03-13 | 6 | bar: 2022-02-07 R to 2022-02-07 U
M2 Data Cleaning | Minjae Lee | 2022-03-07 | 2022-03-13 | 6 | bar: 2022-02-07 R to 2022-02-07 U
M2 Data Visualization | Karishma Rana | 2022-03-07 | 2022-03-13 | 6 | bar: 2022-02-07 R to 2022-02-07 U
M2 Feature Reduction | Joshua Ng | 2022-03-07 | 2022-03-13 | 6 | bar: 2022-02-07 R to 2022-02-07 U
M2 Coding & Implementation | Minjae Lee | 2022-03-13 | 2022-03-30 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-07 U to 2022-03-14 U; 2022-03-28 M to 2022-03-28 W
M2 Results Evaluation | Kayla Hunt | 2022-03-30 | 2022-04-01 | 2 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-28 W to 2022-03-28 F
Midterm Report | All | 2022-03-31 | 2022-04-05 | 5 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-28 R to 2022-04-04 T
Final Report
Model 3 (M3) Design & Selection | All | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 M to 2022-03-14 U
M3 Data Cleaning | Karishma Rana | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 M to 2022-03-14 U
M3 Data Visualization | Youngho Lim | 2022-03-31 | 2022-04-06 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-28 R to 2022-04-04 W
M3 Feature Reduction | Kayla Hunt | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 M to 2022-03-14 U
M3 Implementation & Coding | Minjae Lee | 2022-04-06 | 2022-04-17 | 11 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-04 W to 2022-04-11 U
M3 Results Evaluation | Joshua Ng | 2022-04-17 | 2022-04-20 | 3 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-11 U to 2022-04-18 T
M1-M3 Comparison | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-18 M to 2022-04-25 T
Video Creation & Recording | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-18 M to 2022-04-25 T
Final Report | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-18 M to 2022-04-25 T